## Valve_Plan
Valve_ID | Order_ID | Customer | Valve_Type | Dispatch_Date | Assembly_Date | Value_Cr | Priority | Status | Remarks
V-100 | O-100 | Acme Pumps | Gate | 2026-05-01 | 2026-04-22 | 1.25 | A | ACTIVE | Golden full-kit HBM/VTL valve
V-200 | O-200 | Beta Process | Globe | 2026-05-02 | 2026-04-24 | 0.5 | B | ACTIVE | Golden full-kit subcontract candidate
V-300 | O-300 | Gamma Energy | Ball | 2026-05-04 | 2026-04-28 | 0.75 | C | ACTIVE | Golden assembly-risk valve

## Component_Status
Valve_ID | Component_Line_No | Component | Qty | Fabrication_Required | Fabrication_Complete | Expected_Ready_Date | Critical | Ready_Date_Type | Current_Location | Comments
V-100 | 1 | Body | 1 | N | Y | 2026-04-21 | Y | CONFIRMED | Stores | Ready for machining
V-100 | 2 | Seat | 1 | N | Y | 2026-04-21 | Y | CONFIRMED | Stores | Ready for machining
V-200 | 1 | Bonnet | 1 | N | Y | 2026-04-21 | Y | CONFIRMED | Stores | Ready for machining
V-300 | 1 | Disc | 1 | Y | N | 2026-04-30 | Y | EXPECTED | Fabrication | Expected after horizon to trigger assembly risk

## Routing_Master
Component | Operation_No | Operation_Name | Machine_Type | Alt_Machine | Std_Setup_Hrs | Std_Run_Hrs | Std_Total_Hrs | Subcontract_Allowed | Vendor_Process | Notes
Body | 10 | HBM roughing | HBM |  | 0 | 8 | 8 | Y | HBM | Heavy roughing
Body | 20 | VTL finish | VTL |  | 0 | 4 | 4 | N |  | Internal finish
Seat | 10 | HBM seat prep | HBM |  | 0 | 8 | 8 | Y | HBM | Can be batched
Bonnet | 10 | HBM finish | HBM |  | 0 | 8 | 8 | Y | HBM | Can be batched
Disc | 10 | VTL finish | VTL |  | 0 | 6 | 6 | N |  | Late component risk

## Machine_Master
Machine_ID | Machine_Type | Description | Hours_per_Day | Efficiency_Percent | Buffer_Days | Active
HBM-1 | HBM | Horizontal boring mill | 8 | 100 | 1 | Y
VTL-1 | VTL | Vertical turret lathe | 8 | 100 | 3 | Y

## Vendor_Master
Vendor_ID | Vendor_Name | Primary_Process | Turnaround_Days | Transport_Days_Total | Capacity_Rating | Reliability | Approved | Comments
VEN-1 | Vendor One | HBM | 0 | 0 | Medium | A | Y | Preferred HBM subcontractor
VEN-2 | Vendor Two | VTL | 2 | 1 | Low | B | Y | Backup VTL vendor